## Rencana Harian
Hari Ke | Tanggal | Hari | Fase | Aktivitas
Hari 1 | 2026-04-13 | Monday | Inisiasi | Setup Flutter Project, Git, & Folder Structure
Hari 2 | 2026-04-14 | Tuesday | Inisiasi | Design UI/UX: High Fidelity Wireframe (Figma)
Hari 3 | 2026-04-15 | Wednesday | Inisiasi | Design UI/UX: Alur User Journey (Requester, Tech, Admin)
Hari 4 | 2026-04-16 | Thursday | Firebase | Setup Firebase Project & FlutterFire Configuration
Hari 5 | 2026-04-17 | Friday | Firebase | Integrasi Firebase Auth & Email Domain Validation
Hari 6 | 2026-04-20 | Monday | Model Data | Pembuatan User Model & Firestore Rules
Hari 7 | 2026-04-21 | Tuesday | Model Data | Pembuatan Ticket Model & Enum Status
Hari 8 | 2026-04-22 | Wednesday | Services | Auth Service: Login & Register Logic
Hari 9 | 2026-04-23 | Thursday | Services | Ticket Service: Create & Read Operations
Hari 10 | 2026-04-24 | Friday | Services | Ticket Service: Update & Delete Operations
Hari 11 | 2026-04-27 | Monday | UI Auth | Implementasi UI Halaman Login
Hari 12 | 2026-04-28 | Tuesday | UI Auth | Implementasi UI Halaman Register & Lupa Password
Hari 13 | 2026-04-29 | Wednesday | State | Setup Provider: AuthProvider
Hari 14 | 2026-04-30 | Thursday | State | Setup Provider: TicketProvider
Hari 15 | 2026-05-01 | Friday | UI Core | Implementasi Global Theme, Colors, & Typography
Hari 16 | 2026-05-04 | Monday | UI Core | Custom Widgets: Buttons, Cards, & Input Fields
Hari 17 | 2026-05-05 | Tuesday | Testing | Unit Testing: Auth Service & Model Validation
Hari 18 | 2026-05-06 | Wednesday | Review | Sprint Review 1: Evaluasi Arsitektur & Auth
Hari 19 | 2026-05-07 | Thursday | Buffer | Bug Fixing & Code Refactoring (Bulan 1)
Hari 20 | 2026-05-08 | Friday | Milestone | Checkpoint 1: Sistem Autentikasi Stabil
Hari 21 | 2026-05-11 | Monday | UI Requester | Layout Dashboard Utama Pemohon
Hari 22 | 2026-05-12 | Tuesday | UI Requester | Halaman Form Input Keluhan (Upload Foto/Deskripsi)
Hari 23 | 2026-05-13 | Wednesday | UI Requester | Halaman Riwayat Tiket Saya
Hari 24 | 2026-05-14 | Thursday | UI Requester | Detail Tiket & Real-time Status Tracking
Hari 25 | 2026-05-15 | Friday | UI Technician | Layout Dashboard Utama Teknisi (Open Tickets)
Hari 26 | 2026-05-18 | Monday | UI Technician | Halaman Detail Tiket & Tombol 'Claim'
Hari 27 | 2026-05-19 | Tuesday | UI Technician | Halaman Tiket 'In Progress'
Hari 28 | 2026-05-20 | Wednesday | UI Technician | Fitur Update Status ke 'Resolved'
Hari 29 | 2026-05-21 | Thursday | UI Admin | Layout Dashboard Admin (Statistik Overview)
Hari 30 | 2026-05-22 | Friday | UI Admin | Fitur Manajemen User (Role Assignment)
Hari 31 | 2026-05-25 | Monday | UI Admin | Filter Tiket Berdasarkan Kategori & Prioritas
Hari 32 | 2026-05-26 | Tuesday | Integration | Menghubungkan UI Requester dengan Ticket Service
Hari 33 | 2026-05-27 | Wednesday | Integration | Menghubungkan UI Technician dengan Ticket Service
Hari 34 | 2026-05-28 | Thursday | Integration | Menghubungkan UI Admin dengan Statistik Firestore
Hari 35 | 2026-05-29 | Friday | Navigation | Perbaikan Alur Navigasi & Role-Based Access Control
Hari 36 | 2026-06-01 | Monday | UI Polish | Animasi Transisi & Loading State (Shimmer Effect)
Hari 37 | 2026-06-02 | Tuesday | UI Polish | Responsive Layout untuk Berbagai Ukuran Layar
Hari 38 | 2026-06-03 | Wednesday | Testing | Uji Coba Alur Tiket End-to-End (Requester -> Tech)
Hari 39 | 2026-06-04 | Thursday | Review | Sprint Review 2: Evaluasi Dashboard & Alur Tiket
Hari 40 | 2026-06-05 | Friday | Milestone | Checkpoint 2: Aplikasi Fungsional (Core Features Done)
Hari 41 | 2026-06-08 | Monday | Notification | Setup flutter_local_notifications (Android/iOS)
Hari 42 | 2026-06-09 | Tuesday | Notification | Logika Notifikasi Saat Tiket Baru Masuk (Teknisi)
Hari 43 | 2026-06-10 | Wednesday | Notification | Notifikasi Update Status untuk Pemohon
Hari 44 | 2026-06-11 | Thursday | Settings | Halaman Profil User (Edit Nama/Foto)
Hari 45 | 2026-06-12 | Friday | Settings | Halaman Pengaturan Notifikasi & Tema
Hari 46 | 2026-06-15 | Monday | Help | Halaman About App & Versi Aplikasi
Hari 47 | 2026-06-16 | Tuesday | Help | Halaman Kebijakan Privasi & Syarat Ketentuan
Hari 48 | 2026-06-17 | Wednesday | QA | Stress Testing & Concurrency Test (Banyak Tiket Sekaligus)
Hari 49 | 2026-06-18 | Thursday | QA | Uji Coba Validasi Email Domain @itb.ac.id
Hari 50 | 2026-06-19 | Friday | QA | Pengujian Notifikasi Saat Aplikasi Background/Killed
Hari 51 | 2026-06-22 | Monday | Bug Fixing | Perbaikan Bug UI/UX (Pixel Perfecting)
Hari 52 | 2026-06-23 | Tuesday | Bug Fixing | Perbaikan Bug Sinkronisasi Data Firestore
Hari 53 | 2026-06-24 | Wednesday | UAT | User Acceptance Testing dengan Civitas SBM ITB
Hari 54 | 2026-06-25 | Thursday | UAT | Analisis Feedback UAT & Perbaikan Cepat
Hari 55 | 2026-06-26 | Friday | Optimization | Optimasi Ukuran APK/IPA & Performa Rendering
Hari 56 | 2026-06-29 | Monday | Doc | Pembuatan Dokumentasi Teknis (README & Code Docs)
Hari 57 | 2026-06-30 | Tuesday | Doc | Pembuatan Manual Book (User Guide)
Hari 58 | 2026-07-01 | Wednesday | Build | Final Build Versi 1.0.0 (Release Mode)
Hari 59 | 2026-07-02 | Thursday | Deployment | Penyiapan APK untuk Distribusi Internal
Hari 60 | 2026-07-03 | Friday | Milestone | Project Handover & Penutupan
Hari 61 | 2026-07-06 | Monday | Stabilisasi | Monitoring Produksi: Crash Report & Analytics (Firebase Crashlytics)
Hari 62 | 2026-07-07 | Tuesday | Stabilisasi | Hotfix Bug Kritis Pasca-Rilis (Minggu Pertama Produksi)
Hari 63 | 2026-07-08 | Wednesday | Stabilisasi | Evaluasi Beban Server & Optimasi Firestore Read/Write
Hari 64 | 2026-07-09 | Thursday | Feedback | Pengumpulan Feedback Pengguna Aktif (Survey In-App)
Hari 65 | 2026-07-10 | Friday | Feedback | Prioritisasi Backlog Fitur Berdasarkan Feedback UAT
Hari 66 | 2026-07-13 | Monday | Fitur Lanjutan | Modul Laporan & Export Data Tiket (PDF/Excel)
Hari 67 | 2026-07-14 | Tuesday | Fitur Lanjutan | Dashboard Analytics: Statistik SLA & Waktu Penyelesaian
Hari 68 | 2026-07-15 | Wednesday | Fitur Lanjutan | Fitur Rating & Ulasan Layanan Teknisi
Hari 69 | 2026-07-16 | Thursday | Fitur Lanjutan | Fitur Chat/Komentar Internal pada Tiket
Hari 70 | 2026-07-17 | Friday | Fitur Lanjutan | Sistem Eskalasi Otomatis untuk Tiket Overdue
Hari 71 | 2026-07-20 | Monday | Integrasi | Riset Integrasi Single Sign-On (SSO) dengan Akun ITB
Hari 72 | 2026-07-21 | Tuesday | Integrasi | Implementasi SSO Login untuk Civitas SBM ITB
Hari 73 | 2026-07-22 | Wednesday | Integrasi | Integrasi Notifikasi Email (SMTP/Cloud Functions)
Hari 74 | 2026-07-23 | Thursday | Integrasi | Testing Integrasi SSO & Email End-to-End
Hari 75 | 2026-07-24 | Friday | Keamanan | Audit Keamanan Firestore Rules & Role-Based Access
Hari 76 | 2026-07-27 | Monday | Keamanan | Implementasi Rate Limiting & Validasi Input Lanjutan
Hari 77 | 2026-07-28 | Tuesday | Keamanan | Penetration Testing Dasar & Perbaikan Kerentanan
Hari 78 | 2026-07-29 | Wednesday | Performa | Optimasi Query Firestore & Implementasi Pagination
Hari 79 | 2026-07-30 | Thursday | Performa | Implementasi Caching Lokal (Offline-First Support)
Hari 80 | 2026-07-31 | Friday | Testing | Regression Testing Penuh Setelah Penambahan Fitur
Hari 81 | 2026-08-03 | Monday | Testing | Automated Testing: Widget Test untuk Modul Utama
Hari 82 | 2026-08-04 | Tuesday | Review | Sprint Review 3: Evaluasi Fitur Lanjutan & Integrasi
Hari 83 | 2026-08-05 | Wednesday | Milestone | Checkpoint 3: Versi 1.1.0 Siap Rilis (Fitur Lanjutan Lengkap)
Hari 84 | 2026-08-06 | Thursday | Build | Final Build Versi 1.1.0 (Release Mode)
Hari 85 | 2026-08-07 | Friday | Deployment | Rilis Update Versi 1.1.0 ke Distribusi Internal
Hari 86 | 2026-08-10 | Monday | Training | Penyusunan Materi Training Admin & Teknisi
Hari 87 | 2026-08-11 | Tuesday | Training | Sesi Training Penggunaan Aplikasi untuk Admin SBM ITB
Hari 88 | 2026-08-12 | Wednesday | Training | Sesi Training Penggunaan Aplikasi untuk Teknisi
Hari 89 | 2026-08-13 | Thursday | Dokumentasi | Finalisasi Dokumentasi Teknis & API Reference
Hari 90 | 2026-08-14 | Friday | Evaluasi | Evaluasi Akhir Proyek & Laporan Pencapaian KPI
Hari 91 | 2026-08-17 | Monday | Milestone | Project Closure: Serah Terima Final & Rencana Maintenance
Hari 92 | 2026-08-18 | Tuesday | Rilis v2.1.2 | Code Freeze & Final Regression Testing Versi 2.1.2
Hari 93 | 2026-08-19 | Wednesday | Rilis v2.1.2 | Perbaikan Bug Minor & Verifikasi Changelog Versi 2.1.2
Hari 94 | 2026-08-20 | Thursday | Rilis v2.1.2 | Final Build & Signing Versi 2.1.2 (Release Mode)
Hari 95 | 2026-08-21 | Friday | Rilis v2.1.2 | Rilis Versi 2.1.2 ke Distribusi Internal & Pengumuman Update
Hari 96 | 2026-08-24 | Monday | Milestone | Monitoring Pasca-Rilis Versi 2.1.2 & Penutupan Sprint